## Backlog 5
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Hengwei | Yinan | Jin Han | Melvin | Ramasamy | Shipra
Team member's mood during the this week's meeting: |  |  | Excited | Excited | Excited | Excited | Excited | Excited
1 | Test Plan | Task Quality Evaluation (After Task Completed) | 9 | 10 | 9 | 8 | 8 | 9 | 9 | 7.6667 | 8.3333 | Melvin |  | Through Discussion | Yes | 5 | Excited | 8.8333
| Estimated Task Priority（0-10） |  | 8 | 10 | 10 | 8 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 7 | 10 | 9 | 6 | 8 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 14 | 14 | 4 | 8 | 5
| Team Member's Confidence about the Task (0-10) |  | 8 | 8 | 9 | 8 | 9 | 9
2 | Test Case & Coverage Report | Task Quality Evaluation (After Task Completed) | 9 | 8 | 9 | 10 | 7 | 9 | 8.3333 | 5.5 | 6 | Shipra | Jin Han | Through Discussion | Yes | 5 | Excited | 8.6667
| Estimated Task Priority（0-10） |  | 8 | 9 | 10 | 7 | 8 | 8
| Estimated Task Difficulty（0-10） |  | 7 | 7 | 10 | 1 | 2 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 7 | 14 | 2 | 2 | 6
| Team Member's Confidence about the Task (0-10) |  | 8 | 9 | 8 | 10 | 10 | 9
3 | CMMI | Task Quality Evaluation (After Task Completed) | 8 | 9 | 9 | 8 | 9 | 8 | 7.8333 | 6.5 | 4.8333 | Ramasamy |  | Through Discussion | Yes | 7 | Excited | 8.5
| Estimated Task Priority（0-10） |  | 7 | 7 | 8 | 9 | 8 | 8
| Estimated Task Difficulty（0-10） |  | 8 | 6 | 6 | 6 | 5 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 4 | 4 | 5 | 5 | 6
| Team Member's Confidence about the Task (0-10) |  | 7 | 9 | 9 | 9 | 8 | 7
4 | Wiki | Task Quality Evaluation (After Task Completed) | 8 | 9 | 10 | 8 | 9 | 9 | 7.5 | 4.8333 | 4.1667 | Melvin |  | Through Discussion | Yes | 5 | Excited | 8.8333
| Estimated Task Priority（0-10） |  | 7 | 6 | 7 | 9 | 8 | 8
| Estimated Task Difficulty（0-10） |  | 3 | 6 | 5 | 8 | 4 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 4 | 7 | 4 | 3
| Team Member's Confidence about the Task (0-10) |  | 10 | 8 | 10 | 9 | 8 | 10
5 | Meeting Minutes | Task Quality Evaluation (After Task Completed) | 10 | 9 | 9 | 8 | 8 | 10 | 7 | 5.5 | 4.8333 | Melvin |  | Through Discussion | Yes | 5 | Excited | 9
| Estimated Task Priority（0-10） |  | 5 | 8 | 8 | 7 | 9 | 5
| Estimated Task Difficulty（0-10） |  | 3 | 5 | 7 | 7 | 8 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 5 | 7 | 4 | 7 | 3
| Team Member's Confidence about the Task (0-10) |  | 10 | 8 | 9 | 9 | 9 | 10
6 |  | Task Quality Evaluation (After Task Completed) | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
7 |  | Task Quality Evaluation (After Task Completed) | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
8 |  | Task Quality Evaluation (After Task Completed) | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
9 |  | Task Quality Evaluation (After Task Completed) | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
10 |  | Task Quality Evaluation (After Task Completed) | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)