## Backlog 2
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Hengwei | Yinan | Jin Han | Melvin | Ramasamy | Shipra
Team member's mood during the this week's meeting: |  |  | Excited | Excited | Excited | Excited | Excited | Excited
1 | SRS | Task Quality Evaluation (After Task Completed) | 8 | 9 | 7 | 8 | 9 | 9 | 8.8333 | 7.1667 | 6.8333 | Hengwei | Yinan Jin Han Melvin Ramasamy Shipra | Through Discussion | Yes | 7 | Excited | 8.3333
| Estimated Task Priority（0-10） |  | 9 | 9 | 9 | 8 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 8 | 5 | 8 | 8 | 7 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 5 | 8 | 7 | 7 | 7
| Team Member's Confidence about the Task (0-10) |  | 8 | 8 | 8 | 9 | 9 | 9
2 | Quality Plan | Task Quality Evaluation (After Task Completed) | 8 | 9 | 7 | 7 | 8 | 9 | 8 | 5.6667 | 5.5 | Hengwei | Yinan Jin Han Melvin Ramasamy Shipra | Through Discussion | Yes | 5 | Excited | 8
| Estimated Task Priority（0-10） |  | 7 | 8 | 9 | 8 | 8 | 8
| Estimated Task Difficulty（0-10） |  | 5 | 5 | 6 | 5 | 6 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 4 | 7 | 6 | 6 | 5
| Team Member's Confidence about the Task (0-10) |  | 7 | 9 | 8 | 7 | 8 | 8
3 | UI | Task Quality Evaluation (After Task Completed) | 9 | 8 | 8 | 8 | 8 | 9 | 7.8333 | 7 | 6.8333 | Jin Han | Ramasamy Shipra | Through Discussion | Yes | 5 | Excited | 8.3333
| Estimated Task Priority（0-10） |  | 9 | 7 | 6 | 9 | 7 | 9
| Estimated Task Difficulty（0-10） |  | 8 | 4 | 8 | 8 | 6 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 5 | 8 | 7 | 6 | 8
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 7 | 6 | 9 | 9
4 | Wiki | Task Quality Evaluation (After Task Completed) | 8 | 10 | 8 | 9 | 9 | 9 | 6 | 2.8333 | 2.5 | Melvin |  | Through Discussion | Yes | 2 | Excited | 8.8333
| Estimated Task Priority（0-10） |  | 7 | 6 | 5 | 5 | 6 | 7
| Estimated Task Difficulty（0-10） |  | 3 | 2 | 4 | 0 | 4 | 4
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 2 | 3 | 2 | 2 | 3
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
5 | Meeting Minutes | Task Quality Evaluation (After Task Completed) | 10 | 10 | 8 | 10 | 10 | 10 | 4.8333 | 2.3333 | 2.1667 | Melvin |  | Through Discussion | Yes | 2 | Excited | 9.6667
| Estimated Task Priority（0-10） |  | 5 | 6 | 3 | 6 | 5 | 4
| Estimated Task Difficulty（0-10） |  | 3 | 1 | 3 | 1 | 2 | 4
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 1 | 2 | 2 | 2 | 3
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
6 |  | Task Quality Evaluation (After Task Completed) | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
7 |  | Task Quality Evaluation (After Task Completed) | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
8 |  | Task Quality Evaluation (After Task Completed) | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
9 |  | Task Quality Evaluation (After Task Completed) | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
10 |  | Task Quality Evaluation (After Task Completed) | [6 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)